## Procedure Deployment
# | Category | Task | Description | Assigned To | Status | Date
1 | Prep | Provide System Admin access to execute Deployment | Provide temp system admin access |  | Done | 19/03/2019
2 | Prep | Turn on the Email Deliverability in Production from 'All emails' to ‘No Emails’ through complete process of deployment. | Turn OFF Email Notification |  | Done | 19/03/2019
3 | Prep | Create ChangeSet in UAT | Create a change set as per the file |  | Done | 19/03/2019
4 | Pre Deployment Steps | Pre Production Validation | Please Refer to 'Pre-Deployment Activities' |  | Done | 19/03/2019
5 | Deploy | Upload ChangeSet to PRODUCTION | Push the ChangeSet from UAT to PRODUCTION |  | Done | 19/03/2019
6 | Deploy | Deploy ChangeSet in PRODUCTION | Validate and Deploy Changeset in PRODUCTION
7 | Deploy | Fix Any Test Class failures | If the Validation step fails due to test class failures, fix the test class and rerun the Validation
8 | Post Deployment Steps | Post Production Validation | Please Refer to 'Post-Deployment_Activities'
9 | Post Deployment Validation | Post Deployment Code Validation | Perform spot checks on the components that has been deployed and ensure the recent code fix are reflected OWD - Check each object settings. Custom Profile - Perform Peer Review on custom profile Field Level Security-FLS - Perform Peer Review on custom field
10 | Post Deployment Validation | Test data in Production | Creation of test data by testers for Smoke testing
11 | Post Deployment Validation | Post Production Validation | QA team to perform Smoke checks
12 | Post Deployment Validation | Clean the test data | Clean the test data created during Smoke testing.
13 | Post Deployment Steps | Turn ON Email Notification | Turn ON Email Notification

## Pre-Deployment_Activities
Step# | Title | Description | User Story
1 | Setup domain to create a lightning components | 1. Go to My Domain 2. Setup and deploy to user domain after checking the availibilty. | Task 1
2 | Enable Multiple currency | 1. Under Company Information > Activate multiple currencies. 2. In Quick Find, serach 'Manage currencies' 3. Under "Active Currencies" add "GBP" from drop down with conversion rate as 1. | Task 1

## Deployment Components
Sr.No. | Type Of Component | Use Status
1 | Application
2 | Custom Objects
3 | Standard_Object fields
4 | Custom_Object fields
5 | Apex Class
6 | Custom Labels
7 | Static Resources&Documents
8 | Lightning_Components
9 | Profiles
10 | Layout
11 | Tabs

## Post-Deployment_Activities
S.No | Type | Steps
1 | Provide access to System Admin profile for N26 app | 1. Open System Admin profile. 2. Edit to provide visible access to "N_26" and you can also make it as default app.
2 | Provide access to System Admin profile for Tabs Products and Product Inventories | 1. Open System Admin profile. 2. Edit to provide Tab access under "Custom Tab Settings" for products and Product Inventories
3 | Edit Case layout in Lightning Experience to put the Product Information component in layout
4 | Verify the FLS of all new fields
5 | Data Load of Products and Product Inventories

## Application
Lightning Experience App | Developer_Name | Description | App Type
N 26 | N_26 | N26 Case Study App | Lightning

## Tabs
Label | Object | User Story
Products | Products | Task 1
Product Inventories | Product Inventory | Task 1

## Custom Objects
Include All Related Components
S.No | Object Name | API Name | New/Existing | Type | Layouts | Record Types | Fields | Buttons & Actions | Tab | List Views | Validation Rules
1 | Products | Products__c | New |  | Yes |  | Yes |  | Yes
2 | Product Inventory | Product_Inventory__c | New |  | Yes |  | Yes |  | Yes

## Standard_Object fields
Field Label | API Name | DataType | Object | Component Type
External Id | External_Id__c | Text(100) (External ID) (Unique Case Insensitive) | Contact | New
Home Country | Home_Country__c | Picklist | Contact | New
Language | Language__c | Picklist | Contact | New
Product | Product__c | Picklist | Contact | New

## Custom_Object fields
Field Label | API Name | DataType | Object | New/Existing
Contact | Contact__c | Master-Detail(Contact) | Product_Inventory__c | New
Products | Products__c | Master-Detail(Products) | Product_Inventory__c | New
ATM Fee in other currencies | ATM_Fee_in_other_currencies__c | Text(18) | Products__c | New
Card Replacement Cost | Card_Replacement_Cost__c | Currency(18, 0) | Products__c | New
Cost per Calendar Month | Cost_per_Calendar_Month__c | Currency(16, 2) | Products__c | New
Country | Country__c | Picklist | Products__c | New
Product Type | Product_Type__c | Picklist | Products__c | New

## Apex Class
Class Name | User Story
ProductsController | Task 1
ProductsControllerTest | Task 1
CustomerDetails | Task 2
CustomerDetailsTest | Task 2

## Profiles
Name | User Story
System Administrator | Task 1

## Layout
S.No. | Object Name | Layout Name | Object
1 | Site_Survey_Exceptions__c | Products Layout | Products__c
2 | Site_Survey__c | Product Inventory Layout | Product_Inventory__c
3 |  | Contact Layout | Contact

## Lightning_Components
Label | Name | Description | User Story
ProductInformation | ProductInformation | To show product details to Agent on case layout | Task 1

## Translations
Object | Name

## Static Resources&Documents
Document Name | Document Unique Name | Externally Available Image
N 26 | N_26 | Yes